## Slide 1
Quarterly Council
Performance Report
Quarter 3 – 1 January to 31 March 2024
2
3
6
17
20
21
23
Table of Contents
Executive Summary
Adelaide Hills Council Major Projects
Performance by Strategic Goal
Customer Service Standards
Capital Works Performance
Savings Strategies
Quarterly Financial Performance
DRAFT

## Slide 2
Strategic Goal | Performance Indicators | Annual Business Plan Strategic Initiatives
1. Executive Summary
Chart: 
| On Track | Completed | Not Started | Deferred | Behind schedule | Cancelled
Sales | 22 | 3 | 1 | 3 | 1
1 of 3 Targets met or exceeded
3 of 6 Targets met, N/A or exceeded
Chart: 
| on track | Not Started | Completed | Behind Schedule | Deferred
Sales | 8 | 1
Chart: 
| On Track | Not Started | Completed | Behind Schedule
Sales | 1 | 1
Chart: 
| On Track | Not Started | Behind Schedule | Completed
Sales | 6
Chart: 
| On Track | Not Started | Completed | Deferred | Behind Schedule
Sales | 5 | 1
Highlights
Customer Service Standards
9
Targets met or exceeded
1
Target not met
7
N/A or No Incidents reported
Capital Performance
The primary focus of this quarter has been on tendering projects that were designed earlier in the year, and continuing delivery of asset renewal programs.
Built Environment
Community Wellbeing
Economy
Natural Environment
Organisation
After almost 10 years in development, the Coolamon Sculpture was officially unveiled at Federation Park, Gumeracha by Deputy Mayor Nathan Daniell.
Implementation of the new Customer Relationship Management System commenced in February which included vendor workshops and the first steps in planning and designing the technical transition journey and customer experience tools – such as mock up of the Customer portal.
Council supported the Woodforde community to hold a community picnic in March with 30 attendees. The community were proud of this event and connections they made. They are now looking to establish an ongoing community group with the mentorship of the Morialta Residents Association.
The first steps in representation review have commenced by appointing CL Rowe and Associates to conduct the review. The review is a legislative requirement which purpose is to determine if the community would benefit from an alteration to the current ward structure. A key factor in this year’s review will be the new requirement that Councils have a maximum of 13 elected members and may be scaled based on the size of a Council.
3 of 3 Targets met, N/A or exceeded
$5.1m
of infrastructure delivered
In Progress (22)
Completed (3)
$6.8m
of works ordered
Not Started (1)
Behind Schedule (3)
In Progress (8)
Deferred (1)
In Progress (1)
In Progress (6)
In Progress (5)
Completed (1)
1 of 2 Targets met or exceeded
3 of 3 Targets met, N/A or exceeded
Cancelled (1)
Completed (1)

## Slide 3
Kerbside bin system collection frequency change and rural FOGO trial
Council is undertaking a 12-month food organics and garden organics (FOGO) trial in collaboration with our Waste Management Partner.
Over 600 households and a small number of businesses in parts of Woodside and Lenswood will trial the new kerbside bin collection systems. This includes a new FOGO bin for rural households and a change in the collection frequency of organics bins and landfill bins, which aims to improve the food waste diversion from landfill.
Latest News
Jul 23
Trial is ongoing with all information sessions and prep work successfully undertaken.
Commence planning & scope
= On Track
Legend:
= Completed
= Behind Schedule
2. Adelaide Hills Council Major Projects
FABRIK Development
The FABRIK Development Project involves upgrading and enhancing the former Onkaparinga Woollen Mills site at Lobethal to create an arts and heritage hub in the central Adelaide Hills.
Submit Planning Documentation for approval
Procurement phase
Obtain full Building and Development approval and award construction contract
Begin site works
Oct 21 – Dec 21
Jan 22 – Mar 22
Latest News
Works are progressing well in spite of delays in materials and lack of available trades, including the prolonged timeframe for scheduling of the replacement SAPN transformer.
Key activities during the quarter include:
Installation of windows, auto doors, IT cabinet and ceiling in the pavilion
Internal painting completed in the pavilion and in buildings 14 and 20.
Installed cabinetry and bathroom and kitchen fittings in Building 14
Floor removed in building 14 after discovery of timber rot and replacement timbers have been sourced
Repointing completed and concrete pavement replaced on external of building 21
Skybridge installed and walkway form work scheduled for installation to enable engineers inspection prior to concreting
Installation of HVAC system, glass entry, auto doors, lower level stair cases, IT cabling and cabinetry in building 20
Apr 22 – Jun 22
Jul 22 – Sep 22
Sep 22 – Dec 23
Construction completion
(New date Mar 2024)
Oct 23
Sep 23
Sep 23
Oct 23
Two community information sessions to be undertaken
Identify areas for trial
Initial communications and welcome pack provided to trial participants
Trial Commencement
Sep 24
Evaluate Trial Performance
Dec 24
Consider trial outcomes and make recommendation to Council
Oct 24
Prepare trial review report

## Slide 4
Electric vehicles and charging stations
Funding has been provided to enable the purchase of approximately 12 electric vehicles (EV) during 2023-24 as well as installation of the supporting charging infrastructure.
= On Track
Legend:
= Completed
= Behind Schedule
Purchase orders placed
Arrival of first Electric Vehicles
Strategic Review of Charging Infrastructure
Engage Contractor to Install Charging at Stirling
Install Charging Infrastructure at Heathfield Depot
Dec 22
Sept 23
Dec 23
Latest News
All Electric Vehicles (14 in total) have been delivered.
Small EV chargers have been installed at the Woodside Office and the Garrod Office.
The tender has been let for the installation of 5 EV chargers at the Stirling Office. Following successful tender award, it is anticipated that the EV chargers will be installed during April 2024, but will not be operational until the Main Switchboard has been upgraded potentially in June.
Implement activities from “Our Watch Toolkit for Local Government”
In July 2023, Council adopted an implementation plan based on the “Ourwatch Toolkit for Local Government”.
The aim of the toolkit is to prevent violence against women and their children through a range of strategies including those with an organisational focus. This is followed by work with the community to raise awareness and to undertake population based prevention activities.
Latest News
Establish an internal working group
Develop a workplace safety plan (WSP) & internal Domestic Family Violence (DEV) Policy
Oct 23
With expert support from the Our Watch Institute (OWI), we have commenced the Gender Equity Audit process, which involves a Workplace Equality & Respect Employee Survey planned for April 2024; Workplace Gender Equality Data Analysis which is currently in progress; and focus group meetings
Staff members attended the 'Lessons in Disaster' Training in March, which was delivered by Gender and Disaster Australia. This training increased our capacity to identify, respond to and prevent the harmful impacts of gendered expectations in disaster.
Nov 23 – Jun 24
Remaining Electric Vehicles Received
Nov 23
Sept 23
Jun 24
Finalise construction of Charging Infrastructure at Stirling
= Not Started
Jun 24
Make a statement of commitment & communicate to workforce
Sep 23
Communicate statement to community
Nov 23
Conduct an internal gender equity audit
Develop a Gender Equity Action Plan
Community collaboration on preventative initiatives
Nov 23 – Jun 25
Implement prevention initiatives with stakeholders
Stage 4 – Share & improve
2025
Nov 23 – Jun 24
Nov 23 – Jun 24
Nov 23 – Jun 25

## Slide 5
Towards Community Led Emergency Resilience Program (TCLERP)
Following on from the Community Resilience and Readiness pilot, the program has evolved to focus on community led emergency preparedness. The name of the program also changed to be Toward Community Led Emergency Resilience Program (TCLERP).
The program has several areas of focus including:
Community Engagement
Psychological and emotional emergency preparedness community education
Recovery ready halls project – emergency preparedness for select community facilities
Vegetation management project – ensuring practices are based on best fire science and within shared land owners existing capacity
Latest News
Public consultation for new Bushfire Mitigation Landscape Strategy
Revise Readiness, Recovery and Resilience content on AHC's website to align with the CFS’s 2023-24 bushfire awareness campaign
Jan 24
Jul 23 - Feb 24
The Bushfire Mitigation Strategy - developed by the Landscape Management Project Officer in the Community Resilience Team, was endorsed by Council on the 26th March.
Preparation for the the inaugural South Australian Disability Inclusive Emergency Planning forum to be held in the Adelaide Hills has been completed
In collaboration with the Queensland Disability Network , we facilitated the P-CEP Peer Leadership Program with local communities to help enhance their skills
The majority of successful community applicants for Recovery Ready Halls funding have completed and acquitted their Recovery Ready projects
Community Resilience Officers continue to co-present at community information sessions in partnership with the CFS, including a preparedness breakfast for children and families at Basket Range
The Towards Community Led Emergency Preparedness project has been announced as a finalist in the LG Professionals Excellence in Emergency Management Award.
= On Track
Legend:
= Completed
= Behind Schedule
Jul 23 – Mar 25
Continue to support the running of the Adelaide Hills Community Action Bushfire Network (AHCABN) community network
Support psychological and emotional emergency preparedness community education
Recovery ready halls project – emergency preparedness for select community facilities
Jul 23 – Mar 25
Jul 23 – Mar 24
Coordinate RediCommunities Workshops in 8 communities in partnership with the Australian Red Cross
Build the capacity of council's emergency management and recovery processes
Mar 25
Mar 25

## Slide 6
3. Performance by Strategic Goal
Highlights
Disibility Discrimination Act (DDA) Upgrades Minor - Access upgrades region wide for compliance
The construction plans for the improved DDA access to The Summit Community Centre were received in March and a request for quote has been sent out.
Works expected to commence in mid-May 2024 if quote is process is successful.
Cemeteries Upgrades
Planning underway for the official opening of the Natural Burial Ground at Kersbrook Cemetery.
New signage to be installed at Kersbrook Cemetery
Stirling Cemetery Expansion Project is progressing. Availability of contractors to complete works continues to be a challenge
Installation of further Electric Vehicle charging stations
Small EV chargers have been installed at the Woodside Office and the Garrod Office.
The tender has been let for the installation of 5 EV chargers at the Stirling Office. The EV chargers will installed in the week of the 8-12 April 2024 but will not be operational until the Main Switchboard has been upgraded. this is likely to happen in June.
Place making and community planning
Supported a Woodforde community group to host a community picnic in March which had 30 attendees. The community were proud of this event and connections they made. They are now looking to establish an ongoing community group with the mentorship of the Morialta Residents Association.
A sustainable and strategic framework for supporting all community groups in the hills is being considered to help address the challenge of limited resourcing.
Planning underway for a community forum on 30 April for residents of Teringie, Rostrevor and Woodforde.
Carbon Management Plan - Energy upgrades, Battery & Efficiency Actions
Tender process on changing LED lighting for 35 facilities is currently underway.
Building Upgrades – minor
The addition at the Uraidla red shed has been completed.
New Dog and Cat Facility
The Cat holding facility is now in place and Council is waiting on cat housing to be delivered.
Dog holding is to be expanded by mid April to allow Council to hold dogs for longer periods with enrichment.
= On Track
Legend:
= Not Started
= Completed
= Behind Schedule
= Deferred
= Not a Strategic initiative

## Slide 7
2. Performance by Strategic Goal
Risks & Challenges
Feasibility studies for future projects
No feasibility studies are expected to require expenditure during this financial year therefore the project has been marked as cancelled.
Review the Carbon Management Plan
The meeting with Green Industries SA was undertaken in February 2024 and the RFQ on the review of the CCMP and the new plan was released. A consultant has now been engaged and a Council Workshop planned for the 16 April 2024.
Delays during the process mean the Final Plan will be completed in December 2024 after a community consultation process in Oct/Nov 2024
Houghton Recreation Grounds Facility Contribution
The Houghton, Hermitage, Inglewood and Paracombe Memorial Park Committee’s application to the Office for Recreation, Sport and Racing for the Houghton Hub project was unsuccessful. Staff are currently working with stakeholders to understand next steps for the project.
Next Step planning for Adelaide Hills War Memorial Swimming Centre, Woodside
Due to competing Council priorities, feasibility study was only able to be presented to Council in Feb 2024
= On Track
Legend:
= Not Started
= Completed
= Behind Schedule
= Deferred
= Not a Strategic initiative
Performance Indicators
Delivery of capital works program
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 76 | 14 | 10
TBD
Target
≥ 90%
​​Calculations still in progress due to some system abnormalities.
Operational tasks completed within the Civil Zone Maintenance Program
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 50 | 30 | 20
50%
Target
≥ 80%
Due to a reduction in labour resources, work crews have been combined to ensure adequate staffing levels in a team but resulting in less crews overall. Current priorities are on high risk and/or reactive tasks rather than planned maintenance. Aggressive recruitment is underway to try and fill these vacancies, as well as actively backfilling vacancies with labour hire when available. Once all teams are adequately resourced we will be able to refocus on planned works.
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 90 | 90 | 90 | 90
Result | 84 | 96 | 76
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 80 | 80 | 80 | 80
Result | 60 | 50 | 50 | 50
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 90 | 10
Target
100%
Compliance inspections completed within 10 business days of development completion notification
90%
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 100 | 100 | 100 | 100
Result | 100 | 100 | 100 | 100
31 Development Completion notifications were received in Quarter 3 with 90% of inspections undertaken within 10 business days of receipt of notification. The three that were outside of the 10 days were over the Christmas holiday period and home owners were unavailable for inspections..
= Target Met
Legend:
= Target not met
≥ Greater than or equal to

## Slide 8
Project ID | Strategic Initiatives | Status
B1003 | New Bus Shelter Installation Program | 
B1004 | New and upgraded footpaths | 
B1007 | Recreation Trails & Cycling Routes Framework Implementation | 
B1008 | Amy Gillett Bikeway contribution (Stage 4) | 
B1009 | DDA Upgrades Minor access upgrades region wide (compliance) | 
B2008 | Local Heritage (Privately Owned) Planning and Design Code Amendment | 
B2009 | Place making and community planning | 
B3002 | Implement irrigation systems (renewal / upgrades) | 
B3003 | Investigate and Implement central irrigation control system (region wide) | 
B3004 | Prepare turf and irrigation design/management plans for key bore water use areas | 
B3005 | Carbon Management Plan - Energy upgrades, Battery & Efficiency Actions | 
B3011 | Carbon Offsets Policy | 
B3014 | Review the Corporate Carbon Management Plan | 
B4006 | Asset management - Confirm Web and Connect Licences and Field Devices | 
B4009 | Building Upgrades - minor | 
B4010 | Cemeteries Upgrades | 
B4011 | CWMS Capacity Upgrades (Birdwood & Woodside gravity mains) | 
B4014 | Road Safety Program including co-contribution to Road Blackspot | 
B4015 | Installation of further Electric Vehicle charging stations | 
B4016 | Purchase of Electric Vehicles cars for fleet | 
B4042 | Operational worksite review including forward planning | 
B4043 | Hamilton Hill - Dunfield Estate & Crest Maintenance | 
B4044 | Feasibility Studies for future projects | 
B4045 | Stormwater projects | 
B4050 | Merchants Hill retaining wall | 
B4051 | Croft Road resealing | 
B4052 | Renew the fuel monitoring and delivery system | 
B4053 | Next Step planning for Adelaide Hills War Memorial Swimming Centre, Woodside | 
B4054 | Houghton Recreation Grounds facility contribution | 
Progress on Strategic Initiatives from the Annual Business Plan
= On Track
Legend:
= Not Started
= Completed
= Behind Schedule
= Deferred

## Slide 9
Highlights
Actions from adoption of Aboriginal Place naming Action plan
Filmed a video with Uncle Lewis O'Brien and Uncle Ivan Copley on the naming and use of Kaurna language at Lewis Yarlupurka O'Brien Reserve Hamilton Hill. Once editing and production, the video will be shared on our website.
Tour Down Under 2024
A debrief on the 2024 event was held with Tour Down Under event management staff.
Hitaf Rasheed presented at a council workshop to provide an overview of the results from the 2024 event and the plans for 2025.
Positive Ageing
January and February are traditionally quieter times for services, with activity increasing in March. This is reflected in this quarter's statistics with 1,600 hours of support in and around the home, over 4,000 hours of social support group activities in the community and 445 transport trips.
Play Space Framework Implementation
Construction has commenced at Protea Reserve, Crafers and will commence towards the end of April at Sherry Park, Mylor. Both projects are on track for completion in the 24/25 financial year.
Cultural Development
After almost 10 years in development and collaboration, the Coolamon Sculpture was officially unveiled at Federation Park, Gumeracha by Deputy Mayor Nathan Daniell.
The Hills Harmony Picnic in Gumeracha during March which highlighted performances from Woodside Jamz, Brasilian dancers, Persian dancers and African drummers
Libraries
Introduced a new 'Booktok' collection at the Stirling Library thanks to a donation from the Stirling Community Op Shop. This collection has been established so customers can easily find titles that are popular and trending on TikTok.
= On Track
Legend:
= Not Started
= Completed
= Behind Schedule
= Deferred
= Not a Strategic initiative
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 70 | 2 | 28
7.2
Target
≥ 7
Positive ageing wellbeing score
Average level of self-determined wellbeing of program participants reviewed in the quarter.
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 7 | 7 | 7 | 7
Result | 7 | 7.1 | 7 | 7.2
The overall wellbeing score has risen to be 7.2 in the third quarter of the 23-24 year. The positive comments listed in the wellbeing report (which these statistics are gathered from) refer to people experiencing strong social connections & personally improved personal (mental) health. Where individuals had slightly lower scores, was reflected in physical pain/limitations and also social isolation.
Number of volunteer hours contributed to AHC programs each year
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 3530 | 1270 | 1500
Target
≥ 4,800 per quarter
2893
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 4800 | 4800 | 4800 | 4800
Result | 3276 | 3530 | 3183 | 2893
Performance Indicators
A total of 2893 volunteer hours have been recorded for this quarter, down from last quarter. This follows the National and International trend.
Active volunteer recruitment continues via the AHC website, fortnightly ads in The Courier, Volunteering South Australia & Northern Territory website, SEEK Volunteer, as well as local advertising and word of mouth which still proves to be the best method.
= Target Met
Legend:
= Target not met
≥ Greater than or equal to

## Slide 10
Project ID | Strategic Initiatives | Status
C4006 | Play Space Framework Implementation | 
C4012 | Climate Change Adaption Plan Projects-All hazards emergency management | 
C4021 | Community & recreation facilities framework implementation | 
C4022 | Towards Community Led Resilence Program | 
C4024 | Implement activities from "Our Watch Toolkit for Local Government" | 
C5003 | Actions from adoption of Aboriginal Place naming Action plan | 
C6001 | Fabrik Activation Capital | 
C6003 | Capital Divestment - Capital Cost | 
C6006 | Tour Down Under 2024 | 
Progress on Strategic Initiatives from the Annual Business Plan
= On Track
Legend:
= Not Started
= Completed
= Behind Schedule
= Deferred

## Slide 11
Highlights
Economic Development
Transitioned our Economic Profile data mapping data tool to using the product provided by Remplan.
Facilitated two Adelaide Hills Business Support network meetings to ensure business services to the region are coordinated and optimised
Undertook business visits with businesses in Stirling impacted by the mall fire
Performance Indicators
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100 | 0 | 0
Target
≥ 85%
Percentage of new development application decisions upheld in Council/CAPs favour under appeal
One new Appeal against a CAP decision was lodged in Quarter 3. There are two on-going appeals from Quarter 1 yet to be determined or finalised in the Environment Resource and Development Court.
N/A
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 85 | 85 | 85 | 85
Result
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 85 | 5.1 | 9.9
Target
≥ 85%
Percentage of planning consents completed within statutory timeframes
​​​In Quarter 2 Council issued 193 Planning Decisions with an average assessment time of 15.71 business days.
90.1%
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 85 | 85 | 85 | 85
Result | 95 | 95 | 95.8 | 90.1
Average number of days for building consents
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 8.9 | 11.1 | 10
Target ≤
20 Business
Days
8.99
In Quarter 3 Council issued 71 Building Decisions with an average assessment time of 8.99 business days. Overall 97.18% of Building Consents were issued within statutory timeframes in the Quarter.
Chart: 
| Q4 | Q1 | Q2 | Q2
Target | 20 | 20 | 20 | 20
Result | 13 | 12 | 13.7 | 8.9
= Target Met or N/A
Legend:
= Target not met
= N /A – cant be assessed
≥ Greater than or equal ≤ Less than or equal
Project ID | Strategic Initiatives | Status
E2001 | Review and upgrade Council corporate signage and branding | 
E4001 | Additional Tree safety work required to support the Tour Down under | 
Progress on Strategic Initiatives from the Annual Business Plan
= On Track
Legend:
= Not Started
= Completed
= Behind Schedule
= Deferred
= Not a Strategic initiative
Hosted a retail fundamentals workshop for businesses in Stirling and Woodside
Assisted Stirling Business Association with development of marketing responses to Mall Fire.

## Slide 12
Local Climate Adaptations for landscape conservation
Managed the excessive woody weed infestations which are elevating the fuel levels in council reserves at Mylor Parklands and Bridgewater Recreation Ground
Highlights
Post prescribed burn weed management
Weed control undertaken by contractors at all 10 treated sites.
10 new proposed sites have now been endorsed by Council Members.
Open Space Biodiversity
Commenced the 'Virtual Wildlife Fence' trial in partnership with rescue organisation 1300 Koalaz with the aim of reducing wildlife strike at collision 'hotspots' within the Council road network.
Undertook rabbit biocontrol across 5 reserves - Woorabinda, Lobethal Bsuhland Park, Candlebark Reserve, Mylor oval, Mylor Parklands, The Deanery.
Facilitated the South Australian Feral Deer Eradication Program 2022-2032
= On Track
Legend:
= Not Started
= Completed
= Behind Schedule
= Deferred
= Not a Strategic initiative
Performance Indicators
Percentage of nuisance and litter queries resolved
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 90 | 2.6 | 7.4
92.6%
Target
≥ 90%
Chart: 
| Q3 | Q4 | Q1 | Q2
Target | 90 | 90 | 90 | 90
Result | 86 | 92 | 83 | 85.5
Number of community education actions delivered – actioned vs planned
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 6 | 4 | 5
10
Annual Target ≥ 6
Chart: 
| Q1 | Q2 | Q3 | Q4
Target | 6 | 6 | 6 | 6
Result | 3 | 6 | 10
Tonnes of green organics collected on Green organics days
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 150 | 0 | 50
235
Target
≥ 150 per quarter
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 150 | 150 | 150 | 150
Result | 296 | 180 | 481 | 235
Unresolved CRMs relate to Health (3), Open Space/Civil (12) and Library & Customer Service (2).
= Target Met or N/A
Legend:
= Target not met
= N /A – cant be assessed
≥ Greater than or equal ≤ Less than or equal
Four education events have been held, including FOGO Trial at LGA, education stall at TDU, Uraidla Fair Sustainability Fair and Discover, Play, Bikeway.

## Slide 13
Project ID | Strategic Initiatives | Status
N1007 | Develop a strategy for the management of Council trees across the district | 
N2008 | Develop informative and attractive signage in Council reserves/playgrounds | 
N2010 | Post prescribed burn weed management | 
N2011 | New Dog and Cat facility | 
N3001 | Local Climate Adaptations for landscape conservation | 
N3002 | Resilient community facilities and open space including water fountains | 
N4002 | Kerbside bin system collection frequency change and rural FOGO trial | 
Progress on Strategic Initiatives from the Annual Business Plan
= On Track
Legend:
= Not Started
= Completed
= Behind Schedule
= Deferred

## Slide 14
Highlights
Representation review
CL Rowe and Associates have been appointed to conduct the representation review anticipated to commence in April.
Strategic Plan Development
Workshop was held in March with staff subject matter experts to further progress the ideas and content which will be brought back to Council in May
Building & swimming pool compliance inspections
81 inspections of new developments were undertaken by Council building staff of which 24 were inspections of swimming pools.
Customer Relationship Management (CRM) system upgrade
The required contracts and licences with the vendors have been completed.
Implementation commenced in February with the following items completed:
  discovery workshops with the vendor to capture key information and map out detailed project timeframes.
  identification of request categories to configure the system
  mockup of customer portal
= On Track
Legend:
= Not Started
= Completed
= Behind Schedule
= Deferred
= Not a Strategic initiative
Risks and Challenges
Diversified income study
At this stage there has been limited opportunities to explore this in more detail. This has been marked as deferred and to be considered in the development of the strategic plan.

## Slide 15
Performance Indicators
Number of lost time injuries
3
Annual Target
Actual
0
Decisions (Council resolutions) considered in open Ordinary and Special Council meetings during the period
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 82 | 8 | 10
Target ≥ 90%
83.3%
Council member attendance at ordinary and special meetings for the period
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 82 | 0 | 18
Target ≥ 90%
74.7%
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 90 | 90 | 90 | 90
Result | 92.9 | 94.7 | 81.9 | 83.3
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 90 | 90 | 90 | 90
Result | 82.4 | 81.3 | 83.7 | 74.7
Freedom of Information (FOI) requests received, in progress and completed within the legislated timeframe
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 75 | 0 | 25
Target 100%
100%
Freedom of Information (FOI) External reviews upholding Council’s decisions
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100 | 0 | 0
Target 100%
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 100 | 100 | 100 | 100
Result | 100 | 100 | 75 | 100
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 100 | 100 | 100 | 100
Result | 100 | 100 | 100 | 100
​
One Freedom of Information application received. Completed within legislative timeframes. Two Freedom of Information applications completed.
Nil Internal Review applications received.
100%
During the quarter there were 23 apologies for meetings including leaves of absence.
Employee Turnover
Annual Target
7-15%
16.1%
Actual
Full year target wont be determined until the end of Q4.
= Target Met or N/A
Legend:
= Target not met
= N /A – cant be assessed
≥ Greater than or equal ≤ Less than or equal
Of the 95 decisions resolved by Council, 19 were confidential decisions

## Slide 16
Project ID | Strategic Initiatives | Status
O1005 | GPS for operational vehicles | 
O3002 | Diversified income study | 
O4005 | Representation review | 
O5005 | Resource to manage building & swimming pool compliance inspections | 
O5006 | Strategic Plan Development | 
O5007 | Customer Relationship Management (CRM) system upgrade | 
Progress on Strategic Initiatives from the Annual Business Plan
= On Track
Legend:
= Not Started
= Completed
= Behind Schedule
= Deferred

## Slide 17
4. Customer service standards
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 50 | 50
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 67 | 33
N/A
Target
≥ 75%
5.1 General Customer Standards
Answering Incoming Phone Calls
Contact centre calls answered within 30 sec
Volume of calls = N/A
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 97 | 3
92%
Target
≥ 80%
Updating Customer Details
Details updated
within 5 days
Volume of updates = 86
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 16 | 4
96%
Target
≥ 80%
5.2 Service Specific Standards – Time Based Indicators
New Event Applications
Acknowledgement of receipt within 5 days
Volume of applications = 26
Trend over time
Chart: 
Illegal Burning Complaints
Investigated within
24 hours
Volume of complaints = 0
Trend over time
100%
Target
≥ 80%
Health Complaints
Investigated within
24 hours
Volume of complaints = 2
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100
100%
Target
≥ 80%
Illegally Dumped Rubbish
Rubbish removed
within 3 days
Volume of reports = 89
Trend over time
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 75 | 75 | 75 | 75
Result | 66 | 57 | 64
Volume | 7770 | 9433 | 5043
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 80 | 80 | 80 | 80
Result | 95 | 97 | 97 | 86
Volume | 56 | 105 | 105 | 79
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 80 | 80 | 80 | 80
Result | 83 | 96 | 100 | 96
Volume | 18 | 25 | 7 | 25
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 80 | 80 | 80 | 80
Result | 100 | 82 | 100
Volume | 0 | 11 | 12 | 0
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 80 | 80 | 80 | 80
Result | 50 | 0 | 100 | 100
Volume | 2 | 1 | 1 | 2
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 80 | 80 | 80 | 80
Result | 96 | 100 | 100 | 100
Volume | 68 | 50 | 82 | 89
Results for this quarter are not available. New phone system implemented in November and new reporting process currently being implemented.
≥ Greater than or equal to
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100
Target
≥ 80%
No
Incidents

## Slide 18
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 78 | 22
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 98 | 2
Library Services
Response to requests to purchase materials within 10 days
Volume of requests = 55
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 20
100%
Target
≥ 80%
Dog Attacks
Response within
24 hours
Volume of attack reports = 6
Trend over time
Target
≥ 80%
Wasps
Investigate and action within 7 days
Volume of reports = 0
Trend over time
Development Applications
Approval of fast
track planning
applications within
5 business days
Volume of applications = 6
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 20 | 0
Target
≥ 80%
Missed Bins
Missed bins collected within 2 days
Volume of requests = 0
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 8 | 12
88%
Target
≥ 80%
Request for Bin Repair or Replacement
Requests actioned within 7 days
Volume of requests = 524
Trend over time
Footpath Repairs - Hazardous
Responded and made safe within 24 hours
Volume of repairs = 0
Trend over time
Road Repairs - Hazardous
Responded and made safe within 24 hours
Volume of repairs = 0
Trend over time
76%
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 3 | 17
83%
Target
≥ 80%
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 20 | 0
Target
≥ 80%
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 100 | 0
Target
≥ 80%
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 80 | 80 | 80 | 80
Result | 67 | 66 | 46 | 76
Volume | 67 | 67 | 90 | 55
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 80 | 80 | 80 | 80
Result | 82 | 100 | 100 | 100
Volume | 11 | 11 | 11 | 6
Chart: 
| Q3 | Q4 | Q1 | Q2
Target | 80 | 80 | 80 | 80
Result | 100 | 98
Volume | 24 | 227 | 0 | 0
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 80 | 80 | 80 | 80
Result | 100 | 83
Volume | 5 | 6
Chart: 
| Q3 | Q4 | Q1 | Q2
Target | 80 | 80 | 80 | 80
Result
Volume | 0 | 0 | 0 | 0
Chart: 
| Q3 | Q4 | Q1 | Q2
Target | 80 | 80 | 80 | 80
Result | 93 | 93 | 93 | 98
Volume | 576 | 550 | 1665 | 526
Chart: 
| Q3 | Q4 | Q1 | Q2
Target | 80 | 80 | 80 | 80
Result | 100 | 100
Volume | 0 | 0 | 1 | 0
Chart: 
| Q3 | Q4 | Q1 | Q2
Target | 80 | 80 | 80 | 80
Result
Volume | 2 | 0 | 1 | 0
No
Incidents
Target
≥ 80%
No
Incidents
Result for responses made within the service standard not available as the process for purchase requests has changed.
No
Incidents
This is an adjusted measure for 2023-24 based on deemed to satisfy development applications only to better align with the PDI Act categories and timeframes.
≥ Greater than or equal to
Council no longer deals with wasps on private property
N/A

## Slide 19
Chart: 
| 1st Qtr | 2nd Qtr | 3rd
Sales | 7.7 | 4.3 | 8
Stormwater Repairs - Hazardous
Responded and made safe within 24 hours
Volume of reports = 0
Trend over time
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 98 | 2
Target
≥ 80%
Trees - Hazardous
Responded and made safe within 24 hours
Volume of reports = 76
Trend over time
Target
Less than
12 week
Development Applications
Average consent time from date of receipt
Volume of planning consents = 188
Trend over time
Low Risk Infrastructure Requests – Average Time to Resolve
Volume of Requests = 714
Trend over time
Chart: 
| Q4 | Q1 | Q2 | Q3
Volume | 963 | 889 | 745 | 786
Low Risk Infrastructure Requests – Number of New Requests
Volume of new requests = 786
Trend over time
Overall Volume of Requests
Chart: 
| Q2 21/22 | Q3 21/22 | Q4 21/22 | Q1 22/23 | Q2 22/23 | Q3 22/23 | Q4 22/23 | Q1 23/24 | Q2 23/24 | Q3 23/24
Volume | 1407 | 1755 | 1741 | 1774 | 1965 | 1772 | 2033 | 3087 | 1824 | 1772
Trend in volume of requests/customer cases for which there is an adopted service standard, excluding the volume of phone calls
Chart: 
| 1st Qtr | 2nd Qtr
Sales | 80 | 20 | 0
Target
≥ 80%
No
Incidents
5.3 Service Specific Standards – Other Indicators
Median Consent Time 7 weeks
Resolution time of requests
Average = 91 days
Median = 15.1 days
80th Percentile = 132.92 days
Chart: 
| Q3 | Q4 | Q1 | Q2
Target | 80 | 80 | 80 | 80
Result
Volume | 0 | 0 | 0 | 0
99%
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 80 | 80 | 80 | 80
Result | 98 | 100 | 98 | 99
Volume | 50 | 48 | 48 | 76
Chart: 
| Q4 | Q1 | Q2 | Q3
Target | 12 | 12 | 12 | 12
Average | 15.26 | 10.84 | 12 | 12.83
Median | 6.9 | 6.9 | 6.9 | 6.2
Volume | 234 | 204 | 192 | 188
Chart: 
| Q4 | Q1 | Q2 | Q3
Average | 112 | 34 | 114 | 91
Median | 4.8 | 5.9 | 13.9 | 15.1
80th % | 23.94 | 24.88 | 119.87 | 132.92
Volume | 719 | 714 | 714 | 714
Results are using applications in the state-wide portal
≥ Greater than or equal to
6.2

## Slide 20
5. Capital Works Program
Financial Performance by Asset Category (preliminary numbers)
Highlights
Quarter 3 of 2023-24 FY represents the continuation of the 2023-24 Capital Works Program, with approximately $5.1M of infrastructure delivered, and an additional $6.8M ordered during this period.
The primary focus of this quarter has been on tendering projects that were designed earlier in the year, and continuing delivery of asset renewal programs.
A natural burial ground was constructed at Kersbrook cemetery, complemented by seating and shelter.
Works commenced on the Warren Rd/ Lucky Hit Rd/ Martin Hill Rd intersection Blackspot project.
Many roads throughout the district were patched and resealed, including Cummings Drive, Summertown, and Edwards Hill Rd, Lenswood.
What’s Next
Council's spray sealed roads renewal program will be completed.
Construction will commence on major road projects at Tiers Rd and Croft Rd.
Works to renew and upgrade playgrounds at Mylor and Protea Park will be completed.
Scoping works will commence to inform the 2024/25 Capital Works Program
Asset Category | YTD Actuals $’000 | Annual Revised Budget $’000 | % Spent to Annual Budget $’000s
Bridges | 174 | 1,160 | 15.0%
Buildings | 1,061 | 5,861 | 18.1%
Cemeteries | 53 | 140 | 38.0%
CWMS | 45 | 260 | 17.3%
Footpaths | 725 | 855 | 84.7%
Guardrails | - | - | 0.0%
Kerbing | - | 67 | 0.0%
Local Roads & Community Infrastructure Program (LRCIP) – phase 1 | 314 | 771 | 40.7%
Roads | 3,307 | 7,829 | 42.2%
Sport & Recreation | 562 | 2,083 | 27.0%
Stormwater | 83 | 610 | 13.6%
Other - Retaining Walls, Street Furniture & Traffic Management | 137 | 530 | 25.9%
Fleet | 1,099 | 2,167 | 50.7%
ICT | 447 | 1,035 | 43.2%
Plant & Equipment | 20 | 60 | 33.7%
Project Management Costs | - | 1,511 | 0.0%
Unbudgeted | 17 | - | 0.0%
 | 8,044 | 24,937 | 32.3%

## Slide 21
6. Savings Strategies
Administrative Savings Strategies | Status | Planned | Achieved
Remove media monitoring | Alternate strategy in progress | $14,250 | $0
Media monitoring service extension continues while Council considers the future funding of this service. |  |  | 
Stop taking cash payments | Completed | $9,500 | $9,500
Legal advice has highlighted complex challenges resulting in a pause on “ceasing cash payments”. However, savings have been achieved through implementation of other strategies in the library space resulting from the opening hours reduction. |  |  | 
Remove community arts project money from budget | Completed | $5,300 | $5,300
The budget item for community arts was no longer required and has been removed |  |  | 
Maintenance fees – contractors / materials | On Track | $5,000 | $5,000
Currently reviewing use of in-house staff for cemetery maintenance. Budget adjusted to accommodate. |  |  | 
Remove automatic CPI increase on contract and materials | Completed | $400,000 | $400,000
This has been fully implemented in the adopted budget and will be monitored through the year |  |  | 
Appliance replacement - all facilities | On Track | $10,000 | $10,000
Annual budget for appliance replacement reduced from $30k to $20k and will be monitored through the year |  |  | 
Cleaning contract - reduce frequency | Completed | $33,000 | $20,000
Negotiations on cleaning contract have resulted in $20k savings. No further cleaning savings will be possible. |  |  | 
Reduce no of multifunction devices | On Track | $12,000 | $0
Scoping commenced to reduce the number of devices from 18 down to 8. |  |  | 
Reduce public access computers | On Track | $10,000 | $0
Scoping commenced on renewal program to reduce number of computers and move to a ticketed/booking system for use of remaining computers. |  |  | 
Remove mobile data from laptops and tablets | Completed | $20,000 | $20,000
Mobile data services have been cancelled and staff advised of alternative Wi-Fi solutions if internet required outside of the office. |  |  | 
Reduce People & Culture budget allocation for legal fees | Completed | $15,000 | $15,000
Budget allocation was reduced and will be monitored throughout the year |  |  | 
Salary Savings | Completed | $200,000 | $200,000
Conduct workshops with clubs using internal resources | Completed | $5,000 | $5,000
Public Notification signage install and removal using internal resources | Not On Track | $20,000 | $5,148
The existing contractor arrangement was in place until Mid August 2023 which may impact saving results. |  |  | 
Cease cadet engineer program | Completed | $12,000 | $12,000
Arboculture Consultancy | Completed | $5,000 | $5,000
Reduce consultancy budget and monitor through the year |  |  | 
Data management of utilities and scope 3 components | On Track | $16,000 | TBC
 | TOTAL | $792,050 | $711,948
Chart: 
| Category 1
Series 1 | -962
Series 2 | 110
Column1
Target
$1,072k
Achieved $962k

## Slide 22
6. Savings Strategies
$xx Savings Achieved
Service and Revenue Changes | Status | Planned | Achieved
Tour Down Under - Limit commitment | Completed | $30,000 | $15,000
Budget savings realized were $15,000 due to event cost pressures |  |  | 
Remove funding to attract a major event to the hills | Completed | $20,000 | $20,000
Amend customer service operating hours from 8:30am to 9am | On Track | $12,500 | $12,500
Reduce/remove Adelaide Hills Tourism Funding | Completed | $7,500 | $7,500
New three-year funding agreement was approved and signed June 2023 with funding capped at the 2022-23 level |  |  | 
Reduce community grants | Completed | $10,000 | $10,000
Cease additional digital content offering | Completed | $20,000 | $20,000
No longer purchasing AHC specific digital library content as there is a large content range in SA library network |  |  | 
Digital online streaming/learning resources for language learning and online streaming | Completed | $8,000 | $8,000
Library CD collections - cease new purchases | Completed | $4,000 | $4,000
Printing and photocopying fee increase | On Track | $8,000 | $3,000
Revenue actuals assessed in December 2023 - received additional $3000 compared to December 2022 so largely on track to achieve additional $8000 revenue for the year. |  |  | 
Reduce internal audit program from 4 to 3 audits annually | Completed | $15,000 | $15,000
Cease membership of Murray Darling Basin Association | Completed | $6,700 | $6,700
Increase non resident cemetery fees | Completed | $25,000 | $30,000
Increase outdoor dining permit fees | Completed | $7,000 | $7,000
Increase copyright application fee | Requires attention | $2,000 | $125
The volume of applications have been decreasing as compared to last financial year. This trend potentially due to economic climate impacting communities not needing to access their old house plans for renovations or sales, others chose not to proceed due to the fee. |  |  | 
Reduce community and recreation facilities grants | On Track | $20,000 | $20,000
Implement charge for food premises inspection for new businesses | On Track | $5,000 | $1,960
Standardise fee application for food premises inspection | On Track | $5,000 | $4,060
Cease bird monitoring on reserves following burning | Completed | $5,000 | $5,000
Cease vermin baiting in Stirling, Aldgate and Bridgewater | Completed | $10,000 | $10,000
Heathfield Resource Recovery Centre – Explore options for savings or cost recovery | On Track | $10,000 | $0
The Adelaide Hills Region Waste Management Authority are currently exploring options to reduce costs. No savings identified at this stage. |  |  | 
Waste education - not proceed with high intensity program | Completed | $50,000 | $50,000
Maintain waste education at current levels rather than increase the program as there has not been marked changes in diversion rates in recent years. |  |  | 
 | TOTAL | $280,700 | $249,845
Savings Strategies cont….

## Slide 23
7. Financial Performance
Overall Funding Statement as at 31 March 2024
Note: These figures are preliminary only. The fully reconciled figures will be presented to Council as part of the Budget Review report.

## Slide 24
MORE INFORMATION
63 Mt Barker Road
Stirling SA 5152
08 8408 0400
mail@ahc.sa.gov.au